## TPS
TPS Report - Fall 2019 JavaScript Math Games for School Project Megan Solomon Nick Bobich Andrejs Tomsons
Task | Who | Esimated Time | Risk | Time Spent | Complete | Comments | Added Date | Finished Date
Email Larry about project | All | 15 mins | low | 10 mins | 100% | He replied the next day saying that he will be setting up a meeting with Kapenga and the other group to descuss what the next steps are | 2019-09-09 | 2019-09-11
Find acticles about what makes a good educational game | All | 1 Hr | low | 1 Hr | 100% | Most kids starting at the age of 2 to 17 use technology on a daily basis and 91% are fimilar with video games. | 2019-09-09 | 2019-09-11
Look at standards for 2nd, 3rd, 5th and 6th grade math and reading skills | All | 1 Hr | low | 1 Hr | 100% | Suggested by Larry that we are focusing on 3rd and 5th Grade Math | 2019-09-16 | 2019-09-20
Meet with Larry and Kapenga | All | 2 Hr | low | 1 Hr 30 mins | 100% | We met with Larry and Kapenga to review what we need to do and look over a script for the video made for the many project | 2019-09-16 | 2019-09-20
Build power point presentation | All | 3 Hr | medium | 30 mins | 45% | Started the Design and layout for the power point but need more information | 2019-09-16
Practice coding with phaser | All | 3 Hr | medium | 2 Hr | 100% | Exploring as many examples as possible. Still searching for open source code. | 2019-09-16 | 2019-10-18
Make spikes exploring the fuctionality of creating a game | Andrejs | 12 hours | medium | 5 hrs 30 mins | 60% | Basic movement of the player has been explored. The ability to make scenes, load assets, run sprites, create interactible buttons. | 2019-09-23
Start thinking of ideas for games that follow the script Larry sent us | All | 1 Hr | low | 40 mins | 100% | We are fairly confident with the game we have in mind. Needs to be discussed further as a group. | 2019-09-23 | 2019-10-07
Create a layout for a game that follow the script for adding and subtraction factions | All | 2 Hr | medium | 1 Hr | 100% | We have one game that we feel good about and are going to begin coding this week. Would like to find two more. | 2019-09-23 | 2019-10-18
Build game from textbook to practice development in phaser from start to finish | Nick | 3 Hr | low | 3 Hr | 100% | Following textbook direction to recreate the popular phone game "2048". About half way through the book learning and documenting a lot that will be useful for the games that we are developing | 2019-09-30 | 2019-10-21
Research tools in phaser that will be helpful in recreating the game "Slice" | Megan | 3 Hr | medium | 2 Hrs 30 mins | 100% | "Slice" is the game we are modeling our fraction game after. Found code that will help create a drag function to drag html segments acrossed the screen Phaser has some tools that will help load in all the images at once but hide most of them. This will help the loading speed of the game | 2019-09-30 | 2019-10-21
Had a meeting with larry on Thrusday to discuss progress on project | All | 1 Hr | low | 45 mins | 100% | We need a demo / running mock up of our game for larry to then use and show for grant money | 2019-10-07 | 2019-10-10
Meeting with Larry on October 24th or 25th to walk through game demo and how he can use it | All | 1 Hr | medium |  |  | We are meeting October 25th at 2 pm | 2019-10-14
Talk with Kapenga about meetingwith larry and to see if he is available for it | Megan / Nick | 5 mins | low | 10 mins | 100% | We are meeting October 25th at 2 pm | 2019-10-14 | 2019-10-21
Get familiar with GIMP to create different PNGs for the development of our game | Megan | 30 mins | medium | 1 Hr | 100% | Learned the basics around using GIMP to create my own PNG image for games | 2019-10-18 | 2019-10-20
Design pizza slices for all the different combinations in a 12 piece pizza | Megan | 1 Hr | low | 2 hr | 100% | Created slices of pizza to be out into a sprite for the game | 2019-10-18 | 2019-10-21
Get farmilier with Texture Packer for creating sprite sheets | Nick | 30 mins | medium | 25 mins | 100% | Learned how to create a basic sprite | 2019-10-18 | 2019-10-20
Create spritesheet that has all 12 pieces to the pizza | Megan / Nick | 20 mins | medium | 15 mins | 100% | Created a sprite that contains all the pizza slices for our game so it can load them all at once | 2019-10-18 | 2019-10-20
Start Development of Pizza Slicer | Megan / Nick | 2 Hr | medium |  |  | Create game demo for larry to then display and show for grant money | 2019-10-18
Create randomization functions for pizza slicer | Someone | 30 mins | low |  |  |  | 2019-10-21
Create menu for pizza slicer | Someone | 1 Hr | low |  |  |  | 2019-10-21