## TPS
TPS Report - Fall 2019 JavaScript Math Games for School Project Megan Solomon Nick Bobich Andrejs Tomsons
Task | Who | Esimated Time | Risk | Time Spent | Complete | Comments | Added Date | Finished Date
Email Larry about project | All | 15 mins | low | 10 mins | 100% | He replied the next day saying that he will be setting up a meeting with Kapenga and the other group to descuss what the next steps are | 2019-09-09 | 2019-09-11
Find acticles about what makes a good educational game | All | 1 Hr | low | 1 Hr | 100% | Most kids starting at the age of 2 to 17 use technology on a daily basis and 91% are fimilar with video games. | 2019-09-09 | 2019-09-11
Look at standards for 2nd, 3rd, 5th and 6th grade math and reading skills | All | 1 Hr | low | 1 Hr | 100% | Suggested by Larry that we are focusing on 3rd and 5th Grade Math | 2019-09-16 | 2019-09-20
Meet with Larry and Kapenga | All | 2 Hr | low | 1 Hr 30 mins | 100% | We met with Larry and Kapenga to review what we need to do and look over a script for the video made for the many project | 2019-09-16 | 2019-09-20
Build power point presentation | All | 3 Hr | medium | 2 Hr | 100% | Started the Design and layout for the power point but need more information | 2019-09-16 | 2019-10-21
Practice coding with phaser | All | 3 Hr | medium | 2 Hr | 100% | Exploring as many examples as possible. Still searching for open source code. | 2019-09-16 | 2019-10-18
Make spikes exploring the fuctionality of creating a game | Andrejs | 12 hours | medium | 5 hrs 30 mins | 100% | Basic movement of the player has been explored. The ability to make scenes, load assets, run sprites, create interactible buttons. | 2019-09-23 | 2019-10-21
Start thinking of ideas for games that follow the script Larry sent us | All | 1 Hr | low | 40 mins | 100% | We are fairly confident with the game we have in mind. Needs to be discussed further as a group. | 2019-09-23 | 2019-10-07
Create a layout for a game that follow the script for adding and subtraction factions | All | 2 Hr | medium | 1 Hr | 100% | We have one game that we feel good about and are going to begin coding this week. Would like to find two more. | 2019-09-23 | 2019-10-18
Build game from textbook to practice development in phaser from start to finish | Nick | 3 Hr | low | 3 Hr | 100% | Following textbook direction to recreate the popular phone game "2048". About half way through the book learning and documenting a lot that will be useful for the games that we are developing | 2019-09-30 | 2019-10-21
Research tools in phaser that will be helpful in recreating the game "Slice" | Megan | 3 Hr | medium | 2 Hrs 30 mins | 100% | "Slice" is the game we are modeling our fraction game after. Found code that will help create a drag function to drag html segments acrossed the screen Phaser has some tools that will help load in all the images at once but hide most of them. This will help the loading speed of the game | 2019-09-30 | 2019-10-21
Had a meeting with larry on Thursday to discuss progress on project | All | 1 Hr | low | 45 mins | 100% | We need a demo / running mock up of our game for larry to then use and show for grant money | 2019-10-07 | 2019-10-10
Meeting with Larry on October 24th or 25th to walk through game demo and how he can use it | All | 1 Hr | medium |  |  | We are meeting October 25th at 2 pm | 2019-10-14
Talk with Kapenga about meetingwith larry and to see if he is available for it | Megan / Nick | 5 mins | low | 10 mins | 100% | We are meeting October 25th at 2 pm | 2019-10-14 | 2019-10-21
Get familiar with GIMP to create different PNGs for the development of our game | Megan | 30 mins | medium | 1 Hr | 100% | Learned the basics around using GIMP to create my own PNG image for games | 2019-10-18 | 2019-10-20
Design pizza slices for all the different combinations in a 12 piece pizza | Megan | 1 Hr | low | 2 hr | 100% | Created slices of pizza to be out into a sprite for the game | 2019-10-18 | 2019-10-21
Get farmilier with Texture Packer for creating sprite sheets | Nick | 30 mins | medium | 25 mins | 100% | Learned how to create a basic sprite | 2019-10-18 | 2019-10-20
Create spritesheet that has all 12 pieces of the pizza | Megan / Nick | 20 mins | medium | 15 mins | 100% | Created a sprite that contains all the pizza slices for our game so it can load them all at once | 2019-10-18 | 2019-10-20
Start development of Pizza Slicer | Megan / Nick | 2 Hr | medium | 6 Hr | 80% | Create game demo for larry to then display and show for grant money | 2019-10-18
Create randomization functions for pizza slicer | Someone | 30 mins | low | 15 mins | 100% | Used Math.random to create a random number between a range to choose which slice to appear | 2019-10-21 | 2019-10-26
Create menu for pizza slicer | Someone | 1 Hr | low | 1 Hr 30 mins | 100% | Created a main menu for the game that includes a start button, how to play button, and a quiz button | 2019-10-21 | 2019-10-26
Create quiz for pizza slicer | Megan | 1 Hr | low | 50 mins | 100% | Quiz has three sets of questions that are picked at random and the student takes the quiz to see if they understood adding fractions. | 2019-10-28 | 2019-10-28
Quiz pop up for hints if the answer is wrong | Megan | 1 Hr | medium | 30 mins | 100% | A alert will pop up after the quiz if there is any wrong answers. It also includes a try again button if the student would like to retake the quiz | 2019-10-28 | 2019-10-28
Resize the fractions and pizza slices | Megan | 30 mins | low | 15 mins | 100% | Need to make the facrtions bigger and also some of the slices have a white line under them again. | 2019-10-28 | 2019-11-02
Create buttons for menu | Megan | 25 mins | low | 20 mins | 100% | Creating three buttons for the menu for the user to click on | 2019-10-28 | 2019-11-02
Have a group meeting to discuss midterm check, powerpoint, and game progress | All | 1 Hr | low | 1 Hr 30 mins | 100% | Looked over things together and talked about what we need to still do for the midterm check | 2019-10-28 | 2019-10-31
Math in game for calculating adding slices | Nick | 2 Hr | medium | 1 Hr | 100% | Verified that addition of slices is correct and functions as expected | 2019-11-04 | 2019-11-07
Editing all the fraction and slice images again | Megan | 30 mins | low | 30 mins | 90% | Cleaning up images because unexpected lines are appearing | 2019-11-04 | 2019-11-06
Rules for the game | Nick | 2 Hr | medium | 1 Hr | 100% | Added a scoring system for the game, may need to be improved | 2019-11-04 | 2019-11-07
Meeting with Larry and Kapenga | All | 1 Hr | low | 1 Hr 30 mins | 100% | Meeting went well. Demo for Larry was successful. He likes what we have and we discussed additional features that will be implemented before the end of the semester | 2019-11-04 | 2019-11-08
Add a difficult mode to make the game more challenging | All | 4 Hr | low |  | 100% | Added a diffcult mode that takes away the slice visuals to force the user to added the fractions | 2019-11-11 | 2019-11-18
Evaluate scoring system for possible changes | NIck | 2 Hr | low | 1 Hr | 50% | Not sure until further testing | 11/112019
Create video for demo and how to play | Megan | 2 Hr | medium |  |  |  | 2019-11-11
Have Megan's family test the game | Megan | 30 mins | low | 1 Hr | 100% | They enjoyed the game but gave me a lot of feedback on what more we could do | 2019-11-11 | 2019-11-17
Debug animation | Nick | 3 Hr | High | 6 Hr | 100% | animation was not working at all. Then finially got the animation to work. We discovered that the game was ending unexpectingly beucase it was check for gameover before it needed to | 2019-11-11 | 2019-11-17
Have meeting with database group to integrate game into their system as well as to test our scoring storage | All | 2 Hr | medium | 30 mins | 100% | Showed Kapenga our game demo he gave us some feedback on changes that we should make to be user friendly | 2019-11-11 | 2019-11-18
Make more images such as, expert mode button, change the background for the title screen and game over screen, Change the take quiz button, and add a play again button | Megan | 1 Hr | low | 1 Hr 30 mins | 100% | All buttons have been implemented and are functioning correctly | 2019-11-18 | 2019-11-21
Meet with Kapenga's son for some more suggestions for our game | All | 1 Hr | low | 2 Hr | 100% | He gave us some great suggestions and we were able to replicate his design ideas and implement them successfully | 2019-11-18 | 2019-11-21
Debug reset/play again button | Nick | 2 Hr | medium | 1 Hr | 100% | We needed to make sure that the reset and play buttons take you back to the mode that you started in. The buttons need to be able to identify whether you started in normal mode or expert mode | 2019-11-21 | 2019-11-22
Add the game to AWS | Nick / Megan | 1 Hr | medium | 4 Hr | 100% | We did this so that anyone who would like to test or demo the game can access it from anywhere | 2019-11-22 | 2019-11-24
Add dynamic hints to the game | Nick / Megan | 4 Hr | medium | 4 Hr | 100% | Hints now reflect the math that the student is actually attempting to solve | 2019-11-25 | 2019-12-09
Meet with the team | All | 2 Hr | low | 2 Hr | 100% | Our final meeting is complete. Our client and advisor are both satisfied with our project and we have a few things to finish up for them post graduation | 2019-11-25 | 2019-12-11