## TPS
TPS Report JavaScript Math Games for School Project Megan Solomon Nick Bobich Andrejs Tomsons
Task | Who | Esimated Time | Risk | Time Spent | Complete | Comments | Added Date | Finished Date
Research 5th grade math skills | All | 1 hr | low | 30 mins | 100% | We researched the expected outcomes of 5th grade math and we recieved a copy of the michigan and minnesota state standards for all grades | 2019-03-18 | 2018-03-25
Look for games that reinforce these skills | All | 1 hr | low | 30 mins | 100% | Found some basic 5th grade math games that are popular and have found a few examples to show the client | 2019-03-18 | 2019-03-25
Find open source games to potentially use in our project or for reference | All | 1 hr | low | 30 mins | 100% | Still need to google some more ways to find open source code and find what games are out there for us to use | 2019-03-18 | 2019-04-15
Create/Find a framework that will fit with our requriements | All | 45 mins | low | 15 mins | 100% | Started looking at Frameworks to potentionaly use | 2019-03-27 | 2019-04-25
Talk with other group about storing student progess into their database and how to go about that. Bring up possibility of keeping track of highscore for each student | All | 25 mins | low | 1hr | 50% | Had a meeting on Tuesday 4/02/2019 @ 2pm with the full group to dicuss some specifications for the database | 2019-03-27
Create spikes and a layout of the different math topics and games associated with that topic. | Megan | 25 mins | low | 45 mins | 100% | Started making an organized word document that shows each claim and its sub-standards so we have a better understanding of what our games need to focus on and also so that the standards are easier to read | 2019-03-27 | 2019-04-20
Email client examples of what we are looking at creating or borrowing if open source | All | 30 mins | low | 25 mins | 50% | Did some more research on games that we can possibly use. Still need to find more that are popular to show the client. This is going to take more time than originally anticipated because we were originally making a list of games that focus on 6th grade standards but now we need to find games that focus on 5th grade standards | 2019-04-12
Mock Up for client and teacher to see | All | 3 hours | low | 3 hr 30 mins | 100% | Created a simple mock up html webpage that shows the basics of what we plan to do and how we are going to display it | 2019-04-25 | 2019-04-25